Assignment 1

- Step 1: Identify all tasks required to complete the project

- Step 2: Determine the sequence of tasks

- Step 3: Estimate the duration of each task

- Step 4: Draw a network diagram

- Step 5: Identify the critical path

- Step 6: Calculate the float

- Step 7: Monitor the critical path

Problem 1
The following details are available regarding a project:

| Activity | Predecessor Activity | Duration |
| --- | --- | --- |
| A | - | 3 |
| B | A | 5 |
| C | A | 7 |
| D | B | 10 |
| E | C | 5 |
| F | D,E | 4 |

Problem 2

| Activity | Duration (in weeks) | Precedents |
| --- | --- | --- |
| A | 6 | - |
| B | 4 | - |
| C | 3 | A |
| D | 4 | B |
| E | 3 | B |
| F | 10 | - |
| G | 3 | E,F |
| H | 2 | C,D |

Problem 3

| Activity | Immediate Predecessors | Activity Times (w k s) | Responsibility |
| --- | --- | --- | --- |
| St. John’s Hospital Project | blank | blank | Kramer |
| Start | blank | 0 | blank |
| Organizing and Site Preparation | blank | blank | Stewart |
| A. Select administrative staff | Start | 12 | Johnson |
| B. Select site and survey | Start | 9 | Taylor |
| C. Select medical equipment | A | 10 | Adams |
| D. Prepare final construction plans | B | 10 | Taylor |
| E. Bring utilities to site | B | 24 | Burton |
| F. Interview applicants for nursing and support staff | A | 10 | Johnson |
| Physical Facilities and Infrastructure | blank | blank | Walke |
| G. Purchase and deliver equipment | C | 35 | Sampson |
| H. Construct hospital | D | 40 | Casey |
| I. Develop information system | A | 15 | Murphy |
| J. Install medical equipment | E,G,H | 4 | Pike |
| K. Train nurses and support staff | F, I, J | 6 | Ashton |
| Finish | K | 0 | blank |