## Slide 1: Project Schedule Management
LECTURE # 7

## Slide 3
PERT stands for Program Evaluation Review Technique and it is the most common form of three-point estimation.
It was developed jointly by the U.S. Navy, Lockheed Martin and the consulting firm of Booz, Allen and Hamilton working on the Polaris nuclear submarine project during the 1950s.
PERT is one of the most commonly used techniques used along with Critical Path Method (CPM) to estimate the minimum time needed to complete a project.

## Slide 7: EXAMPLE

## Slide 16: Appendix 7.1
PERT and PERT Simulation

## Slide 17: PERT—Program Evaluation Review Technique
Assumes each activity duration has a range that statistically follows a beta distribution.
Uses three time estimates for each activity: optimistic, pessimistic, and a most likely to represent activity durations.
  Knowing the weighted average and variances for each activity allows the project planner to compute the probability of meeting different project durations.

## Slide 18: Advantages of PERT
1.Increased accuracy over one-point estimates
  Usually, when asked to provide estimates, the team members think about a single number and pad it as much as they possibly can. They realize that the project manager may cut down on it. That is definitely not the way to get good estimates.
2. Better commitment from the project team members
  Since the estimate is provided by the team members, they are much more accountable.
3. Realistic estimates
  By estimating in a range, you are able to generate a more realistic estimate. This is a clear indication to the stakeholders and project sponsor that the estimates are not 100% accurate. There are risks that have been considered that may impact the amount of time and cost the task will take. This approach addresses some of the team members’ uncertainty that is associated with the estimation process

## Slide 19: Activity and Project Frequency Distributions
FIGURE A7.1

## Slide 20: Activity Time Calculations
The weighted average activity time is computed by the following formula:
(7.1)

## Slide 21: PERT
Construct network diagram and determine the critical path
Determine expect project length
Determine Mean/Expected time & Variance of the project
What is the probability of completing the project on or before 22 weeks

## Slide 23
Variance
0.11
0.44
1
0.11
1.77
1.77
1
1
1
1
tp
to
2
2
6
3
4
3
2
5
3
5
5
3

## Slide 24
FINISH
START

## Slide 25
0
A
6
4
4
4
6
10
6
D
8
4
4
10
2
12
0
B
3
3
3
3
3
6
0
C
4
0
0
0
4
4
3
E
6
3
3
6
3
9
4
F
9
0
0
4
5
9
4
G
7
10
10
14
3
17
8
I
13
4
4
12
5
17
9
H
14
0
0
9
5
14
14
J
17
0
0
14
3
17
FINISH
START

## Slide 26: Activity Time Calculations (cont’d)
The variability in the activity time estimates is approximated by the following equations:
The standard deviation for the activity:
The standard deviation for the project:
Note the standard deviation of the activity is squared in this equation; this is also called variance. This sum includes only activities on the critical path(s) or path being reviewed.
(7.2)
(7.3)

## Slide 27: Probability of Completing the Project
The equation below is used to compute the “Z” value found in statistical tables (Z = number of standard deviations from the mean), which, in turn, tells the probability of completing the project in the time specified.
(7.4)

## Slide 28: Z CALCULATION
Z= P (x< 22)= x- -
Step 1:
Critical Path: C-F-H-J
Step 2:
SD= 1+1.77+1+1
4.77 =2.18
Step 3: Computing Values
22-17
= _____=2.29
2.18
Step 4: Look at Z Table to find value
0.9890 or 98.90 %

## Slide 29: Hypothetical Network (cont’d)
FIGURE A7.2 (cont’d)

## Slide 30: Possible Project Duration
FIGURE A7.3
0.2514

## Slide 31: EXERCISE
ACTIVITY | PREDECESSOR | DURATION |  |  | MEAN | VARIANCE
 |  | To | Tm | Tp |  | 
A | - | 4 | 4 | 10 |  | 
B | - | 1 | 2 | 9 |  | 
C | - | 2 | 5 | 14 |  | 
D | A | 1 | 4 | 7 |  | 
E | A | 1 | 2 | 3 |  | 
F | A | 1 | 5 | 9 |  | 
G | B,C | 1 | 2 | 9 |  | 
H | C | 4 | 4 | 4 |  | 
I | D | 2 | 2 | 8 |  | 
J | E,G | 6 | 7 | 8 |  | 
a)Construct the project network
b) Find the expected duration and variance of each activity
c)Find the critical path and expected project duration.
d)What is the probability of completing the project on or before 35 weeks